## Backlog
ID | Item | Type | Area | Priority | Est. (days) | Week | Owner | Blocked by | Status | Notes
B1 | Admin view renders for non-admin users | Bug | Dashboard / Auth | P0 | 0.5 | Week 1 | Favour |  | Not started | Access-control defect - verify RLS, not just the render path
B2 | Professional fees calculated at 0.1% instead of 10% | Bug | Budget engine | P0 | 0.5 | Week 1 | Favour | Vanessa alignment (final %) | Not started | Ship as a configurable rate in app_config
B3 | Password reset behaves as auto-login, not a reset | Bug | Auth | P0 | 0.5 | Week 1 | Favour |  | Not started | Token-based reset with expiry and single use
B4 | Payment recording in a stage redirects to main Payments page | Bug | Payments | P1 | 0.25 | Week 1 | Favour |  | Not started | Redirect fix only; full in-stage flow is F10
B5 | Certificate emails send from a personal address | Bug | Notifications | P0 | 0.5 | Week 1 | Favour | Verified Resend sender | Not started | Tied to the infrastructure migration already flagged red
B6 | Invitation email language ignores account language | Bug | Notifications / i18n | P1 | 0.5 | Week 1 | Favour |  | Not started | Resolve locale from recipient account, not sender session
B7 | Help page email link broken; hello@ address invalid | Bug | Support | P1 | 0.25 | Week 1 | Favour |  | Not started
B8 | Support tickets do not reliably notify admin | Bug | Support | P1 | 1 | Week 3 | Favour |  | Not started | Notification is the easy half - the 24h window needs a named owner
B9 | Teams screen pricing display incorrect | Bug | Billing UI | P2 | 0.25 | Week 1 | Favour |  | Not started
B10 | Default 196-day timeline rejected as unrealistic | Bug | Timeline | P1 | 0.5 | Week 4 | Favour | Vanessa alignment | Blocked | Estimate is implementation only, once the rule exists
F1 | Password strength indicator and complexity enforcement | Feature | Auth | P0 | 0.5 | Week 1 | Favour |  | Not started
F2 | Two-factor authentication | Feature | Auth | P0 | 1.5 | Week 1 | Favour |  | Not started | Enrolment, login challenge, recovery codes. TOTP over SMS - see Flags
F3 | Project creation branches on new vs ongoing build | Feature | Creation | P0 | 1.5 | Week 2 | Favour |  | Not started
F4 | Upload existing plans / BoQ on the ongoing-build path | Feature | Creation | P1 | 1 | Week 2 | Favour |  | Not started | Storage and review state only; no document parsing in v1
F5 | Slide-based step UI for floor details | Feature | Creation | P1 | 1.5 | Week 2 | Favour |  | Not started | Must make skipping a floor impossible
F6 | Collect phone and home address before plan selection | Feature | Creation | P1 | 0.5 | Week 2 | Favour |  | Not started | Site location stays out - handled manually at go-live
F7 | Default finishing to Standard | Feature | Creation / Budget | P1 | 0.25 | Week 2 | Favour |  | Not started | Engine keeps 1.45/1.70 multipliers; not user-selectable at creation
F8 | Declutter project dashboard | Feature | Dashboard | P1 | 1 | Week 3 | Favour |  | Not started | Remove payment status, stage progress, predicted timeline; keep cost allocation
F9 | Client dashboard cleanup | Feature | Dashboard | P1 | 0.5 | Week 3 | Favour | Philip: cost-allocation conflict | Blocked | Own projects only; remove upload-evidence
F10 | Record payments inside the stage interface | Feature | Payments | P0 | 1.5 | Week 3 | Favour |  | Not started
F11 | Replace ID upload with payment-name matching | Feature | Verification | P1 | 1 | Week 3 | Favour | SwyChr name-return confirmation | Blocked | Keep the ID path built but dormant, triggered on flag
F12 | Restrict certificates to Jalla Verify tier | Feature | Certificates | P1 | 0.5 | Week 4 | Favour | Philip: already-issued certificates | Blocked
F13 | Rename the Danger section in account settings | Feature | Settings | P3 | 0.1 | Week 1 | Favour |  | Not started | Suggest 'Close account'
F14 | Admin to on-ground verifier communication for stage approvals | Feature | Admin | P1 | 5 | Week 5 | Favour |  | Not started | Phase 1 of the comms build - what the Jalla Verify promise depends on
F15 | In-platform communication replacing WhatsApp, incl. video | Feature | Comms | P2 | 20 | Month 2-3 | Favour |  | Not started
F16 | Payment reporting and bookkeeping integrated with the BoQ | Feature | Reporting | P2 | 20 | Month 2-3 | Favour |  | Not started
F17 | WhatsApp integration | Feature | Comms | P2 | 1 | Week 4 | Favour | Philip payment link | Blocked | Conflicts with F15 direction - thinnest possible wiring
F18 | Resources section content | Feature | Resources | P3 | 1 | Week 4 | Favour | Vanessa source documents | Blocked | Explicitly low priority
F19 | Professional fee and 5% miscellaneous buffer formula | Feature | Budget engine | P0 | 1 | Week 4 | Favour | Philip/Vanessa alignment meeting | Blocked
F20 | Roofing feature | Shelved | Creation | - | 0 | Unscheduled | Favour | Clarity on presentation | Shelved | Suspended - users confused by current presentation
V1 | Provide official resource documents | Dependency | Resources | P3 | 0 | Unscheduled | Vanessa |  | Not started | Unblocks F18
V2 | Define the verification standard process | Dependency | Verification | P1 | 0 | Unscheduled | Vanessa |  | Not started | Unblocks the Jalla Verify approval workflow and F14

## Summary
Groundwork - Beta Feedback Backlog
Source: Beta Testers Feedback Implementation, 3 Sep 2026 (Philip / Favour). Compiled 4 Sep 2026.
Assumption
Dev capacity (days per week, solo) | 5 | Blue = input. Change it and every variance below recalculates.
By type
Type | Items | Dev days
Bug | 10 | 4.75
Feature | 19 | 59.35
Dependency | 2 | 0
Shelved | 1 | 0
Total | 32 | 64.1
By priority
Priority | Items | Dev days
P0 | 9 | 8
P1 | 15 | 13.75
P2 | 4 | 41.25
P3 | 3 | 1.1
Schedule
Week | Items | Dev days | Capacity | Variance
Week 1 | 11 | 5.35 | 5 | -0.35
Week 2 | 5 | 4.75 | 5 | 0.25
Week 3 | 5 | 5 | 5 | 0
Week 4 | 5 | 4 | 5 | 1
Week 5 | 1 | 5 | 5 | 0
Month 2-3 | 2 | 40
Unscheduled | 3 | 0
Total | 32 | 64.1
Reality check
Dev days in Philip's one-week cap |  | 5.35
Dev days in the whole list |  | 64.1
Dev days excluding the two month-scale builds |  | 24.1
Weeks to clear everything except those two builds |  | 4.82
Share of items delivered in week 1 |  | 34.38%
Share of near-term dev days delivered in week 1 (excl. month-scale) |  | 22.2%
Items blocked on someone else |  | 7
Week 1 is deliberately the trust block: the role leak, the fee maths, the reset flow, the sender address, 2FA.
SwyChr / 'Switcher' is not blocked by anything below week 1 and can start in parallel from week 2.
Estimates are solo-dev days for build + self-test, excluding review cycles and meetings. Source: Favour's own in-call estimates where given (F15, F16), otherwise assigned here.

## Flags
Open questions - need Philip's answer
Four of these block code, not just planning.
# | Flag | Needed by | Detail
1 | Cost allocation contradiction | Week 3 | The decisions log says retain cost allocation on the project dashboard AND remove it from the client dashboard. Reading it as: keep at project level, remove from the client home view. One line of confirmation needed.
2 | The one-week cap does not fit the list | Immediate | ~19 dev days outside the month-scale builds; 24 including F14. Either the cap moves or the scope does. The schedule tab is the scope-moves version.
3 | WhatsApp integration vs replacing WhatsApp | Week 4 | Paying to integrate a channel we have committed to replacing. Recommend the thinnest possible wiring and no further investment.
4 | Payment-name matching only verifies card payers | Week 3 | Mobile money and bank transfer on the SwyChr rails may return no verified account name - and SwyChr is the fund custodian, so its KYC posture sets the ceiling, not ours. Confirm what name SwyChr returns before removing anything.
5 | Certificates already issued on Self Verify | Week 4 | Revoke, grandfather, or hide? Revoking is the cleanest incentive and the worst experience.
6 | 2FA channel | Week 1 | SMS to Nigeria and Cameroon is expensive and unreliable. Recommend TOTP with email fallback.
7 | Fee change moves every existing quote | Week 1 | 0.1% to 10% plus a 5% buffer shifts displayed totals by ~15% on every project already in the system, beta testers' included. Recalculate or freeze at the quoted figure?
8 | Timeline logic shape | Week 4 | Is the new timeline a function of floors/footprint/finishing, or a per-project-type table from Vanessa? Different builds.
9 | The alignment meeting is the critical path | Immediate | Unblocks B2, B10 and F19. If it does not land before day 3 of week 4, those three slip.